## Instructions
IN PROJECT AI COMMAND CENTER
Cedar Ridge Medical Office Building ¦ Workbook generated 2026-08-25
How to read this workbook
In Project AI is the project-controls command center from In Project LLC. This workbook mirrors the on-screen Command Center and breaks out every agent and module that contributed to the analysis.
The tabs
Command Center
KPIs, top critical items, and the module-summary tiles — the at-a-glance view.
Risk
The scored risk register from the Risk agent.
Budget
Cost health, forecast, and budget-at-risk items from the Budget agent.
Schedule
Milestones and schedule buffer from the Planning agent.
Documents
Document classification + completeness vs. the documents expected for the phase.
Quality
Recurring QC patterns and one-off findings.
Submittals
Overdue / missing / stale / out-of-sequence submittals.
RFIs
Open RFIs by impact, with 14-day SLA breaches flagged.
Change Orders
Flagged change orders and the scope-creep trend.
Action Items
Concrete next steps, owned and prioritized.
Source
(Hidden) raw KPI + classification data behind the workbook.
Note
Dollar and day figures are risk-adjusted estimates for decision support — validate before acting.

## Command Center
IN PROJECT AI COMMAND CENTER
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
29 / 100 |  | $1,125,085 |  | 67% |  | +39 d
PROJECT HEALTH |  | RISK EXPOSURE |  | CONFIDENCE INDEX |  | PROJECTED SLIP
Top Critical Items
# | Item |  |  |  | Source | Trade | Severity | Impact
1 | Contingency Exhaustion Imminent: P80 Risk Exposure ($498K) Dwarfs Remaining $276K Reserve |  |  |  | synthesis |  | critical | $498,000
2 | Life-Safety Document Gaps (Safety Plan 58% + Fire-Stop NCRs) Compound AHJ Inspection Failure Risk at Close-Out |  |  |  | synthesis |  | critical | $240,000
3 | Steel erection is actively underway at Level 2 without a written Fall Protection Plan (Subpart M), no documented Competent Person for scaffolding, and no site-specific JHA for crane/steel operations. Three near-misses in Zone B in 14 days including an unsecured ladder. OSHA citation exposure is near |  |  |  | risk | Safety | critical | $185,000
4 | RFI-047 → SUB-031 → Curtain Wall Fabrication: A Triple-Linked Critical-Path Blockage |  |  |  | synthesis |  | critical | $185,000
5 | Commissioning Authority Not Retained at 58% Complete: Fire Alarm + Sprinkler Lag Creates CO Denial Risk |  |  |  | synthesis |  | critical | $175,000
Module Summary
risk |  | 15 active |  | 4 critical · 4 high
budget |  | $4.98M / $4.82M |  | At Risk · -3.26% var
submittals |  | 4 / 10 |  | 1 overdue · 2 in review
rfis |  | 6 open |  | 3 past 14-day SLA
change orders |  | +$186K |  | 3.9% of contract · watch
quality |  | 8 findings |  | 3 recurring patterns

## Risk
IN PROJECT AI - RISK IQ
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
ID | Category | Risk | Level | Score | Cost Impact | Sched (d) | Owner
R-001 | Safety | Steel erection is actively underway at Level 2 without a written Fall Protection Plan (Subpart M), no documented Competent Person for scaffolding, and no site-specific JHA for crane/steel operations. Three near-misses in Zone B in 14 days including an unsecured ladder. OSHA citation exposure is near-certain if inspected; a struck-by or fall fatality would halt the project. Likelihood 5 (plan is missing, work is ongoing, near-misses are escalating); Impact 5 (potential fatality, stop-work, criminal/civil liability). | Critical | 25 | $185,000 | 21 | Safety Manager
R-002 | Quality | Three cold-joint NCRs in Zone B Level 2 slab within 14 days (NCR-018, NCR-021, NCR-023) indicate a systemic pour-sequencing deficiency, not an isolated incident. Cold joints in a medical office building slab compromise structural integrity and may require core testing, engineered repair, or partial demolition/replacement. Likelihood 5 (already recurring, root cause not yet resolved); Impact 4 (structural repair, re-inspection, schedule delay, potential engineer-of-record rejection). | Critical | 20 | $120,000 | 25 | Superintendent
R-003 | Schedule | RFI-047 (steel connection detail at grid C-4) has been open 20 days, exceeds the 14-day SLA, and is flagged as a critical-path blocker for Activity A400 (Structural Steel Erection). Steel erection is already 8 days behind schedule with -8 float. Each additional day without resolution adds directly to the project delay and $2,500/day LD exposure. Likelihood 5 (already blocking work today); Impact 4 (critical path, LD exposure, cascading to envelope and MEP). | Critical | 20 | $95,000 | 18 | Project Manager
R-004 | Subcontractor | The drywall subcontractor has been short-staffed for three consecutive weeks (6 of 10 planned workers), Activity A610 is already 11 days behind with -11 float on the critical path, and NCR-022 documents out-of-plumb framing on Level 1 north wing. Persistent understaffing signals subcontractor capacity or financial distress. Likelihood 4 (three consecutive weeks of under-manning; pattern is established); Impact 4 (critical path, quality NCRs, cascading finishes and commissioning delay). | Critical | 16 | $140,000 | 22 | Project Manager
R-005 | Regulatory | Life-safety NCRs are open: NCR-019 (missing fire-caulk at Level 1 corridor penetrations), an unfired electrical junction box (high life-safety punch item), and RFI-052 (fire damper at corridor smoke barrier, submitted 2026-02-24). For a medical office building, AHJ and health department inspections are rigorous; unresolved life-safety deficiencies will fail inspections and delay the Certificate of Occupancy. Likelihood 4 (NCRs are documented, fire-stop work is already non-compliant); Impact 4 (C/O denial, commissioning delay, owner move-in delay, LD exposure). | Critical | 16 | $55,000 | 14 | MEP Coordinator
R-006 | Schedule | RFI-045 (electrical panel location conflict with ductwork in the east wing) has been open 15 days with confirmed cost and schedule impact, and is blocking MEP rough-in coordination (Activity A600, already at -6 float). RFI-052 (fire damper at smoke barrier) was submitted today. Unresolved MEP coordination conflicts on a medical office building—with complex infection-control zoning and pressurization requirements—can cascade into wall closure delays and commissioning failures. Likelihood 4 (RFI-045 already blocking work; east wing rough-in started despite unresolved conflict); Impact 3 (east wing MEP rework, schedule float erosion, potential wall re-open). | High | 12 | $45,000 | 12 | MEP Coordinator
R-007 | Weather | Cedar Ridge, UT is subject to significant winter weather from November through March, including sub-freezing temperatures, heavy snowfall, and freeze-thaw cycles. Active construction through February–March 2026 includes steel erection, concrete pours, and building envelope work—all weather-sensitive. Current temperature is 34°F; concrete cold-weather placement per ACI 306 is required. Existing cold-joint NCRs may be exacerbated by cold-weather pour conditions. Likelihood 4 (February–March in Utah; statistical probability of freeze events is high); Impact 3 (concrete quality failures, steel erection shutdowns, crane wind limits, crew productivity loss). | High | 12 | $35,000 | 8 | Superintendent
R-008 | Labor | The drywall subcontractor's chronic understaffing reflects a broader skilled-labor shortage in the Cedar Ridge/Wasatch Front region during an active construction season. Steel, electrical, and mechanical trades are also tracking below planned manpower on the daily report. If multiple trades are simultaneously under-manned, schedule float will be exhausted and LD exposure will accelerate. Likelihood 3 (regional labor market is tight; daily report confirms under-manning on three trades today); Impact 4 (cascading critical-path delays, LD exposure at $2,500/day). | High | 12 | $60,000 | 15 | Project Manager
R-009 | Cost | The project is already accumulating concurrent delays (steel -8 days, drywall -11 days) with Substantial Completion at 2026-09-30 and LDs of $2,500/day. Total float erosion across critical-path activities (-4 to -11 days) signals the CM contingency ($96,000) and owner contingency ($180,000) may be insufficient if multiple risks materialize simultaneously. Likelihood 3 (multiple concurrent delays already in progress); Impact 4 (contingency exhaustion, LD exposure, owner disputes, lien exposure). | High | 12 | $150,000 | 0 | Project Manager
R-010 | Supply Chain | Medical office buildings require long-lead specialty equipment and materials: medical gas rough-in, HVAC equipment with specific infection-control ratings, fire-rated curtain wall assemblies, and specialty door hardware (RFI-041 open 24 days). Cedar Ridge, UT is a non-major market with limited local supply; freight and lead times are extended. Curtain wall anchor embed question (RFI-049) is open 7 days and affects the envelope start (A500, -10 float). Likelihood 3 (supply chain disruptions remain elevated; Utah location adds freight time); Impact 4 (envelope and MEP schedule gates cannot be met without materials on site). | High | 12 | $55,000 | 14 | Project Manager
R-011 | Design | RFI-047 (structural connection, critical path), RFI-045 (MEP conflict), RFI-049 (curtain wall embed), and RFI-052 (fire damper) are all open with cost or schedule impact. RFI-041 (door hardware) is 24 days open with no resolution. The volume and age of open RFIs on a $4.8M medical office building during active construction suggests incomplete or conflicting construction documents. Continued design ambiguity will generate rework, change orders, and delay claims. Likelihood 3 (6 open RFIs with cost/schedule impact; 2 overdue past SLA); Impact 3 (rework, change orders, schedule float consumed). | Medium | 9 | $30,000 | 7 | Project Manager
R-012 | Permitting | Cedar Ridge, UT AHJ inspections for a medical office building include structural, MEP, fire protection, and health department approvals. With multiple open NCRs and life-safety deficiencies, an upcoming framing or rough-in inspection could result in a failed inspection notice, requiring corrective work and re-inspection before the next phase can proceed. Utah DOPL licensing requirements for medical occupancies add an additional regulatory layer. Likelihood 3 (open NCRs and life-safety punch items are unresolved; inspection is likely within 60 days); Impact 3 (failed inspection halts enclosure and MEP advancement). | Medium | 9 | $20,000 | 10 | Project Manager
R-013 | Geotechnical | Foundations (A300) completed through 2026-01-15 in a Utah winter; freeze-thaw cycles during and after foundation construction can affect sub-slab conditions, perimeter drainage, and any remaining below-grade utility connections. Cedar Ridge area soils in the Wasatch Front region may include expansive clays or variable fill that were not fully captured in the geotechnical report. Any differing site conditions encountered during remaining utility tie-in work trigger AIA A201 §3.7.4. Likelihood 2 (foundations complete, but utility tie-ins remain; Utah expansive soils are plausible); Impact 3 (utility rerouting, underpinning, schedule delay). | Medium | 6 | $20,000 | 7 | Superintendent
R-014 | Utilities | Site grading and utilities (A200) were completed in 2025, but Level 1 corridor electrical rough-in has revealed at least one undocumented penetration/junction box condition (NCR-019, fire-stop missing). During remaining MEP rough-in and above-ceiling coordination, conflicts between undocumented existing utility runs and new MEP systems are possible, especially given the active RFI-045 panel/ductwork conflict. Likelihood 2 (one penetration conflict already found; east wing MEP is just starting); Impact 3 (rework, wall openings, MEP rerouting, inspection delays). | Medium | 6 | $18,000 | 5 | MEP Coordinator
R-015 | Environmental | Cedar Ridge, UT construction sites are subject to UPDES stormwater permit (SWPPP) requirements. With site grading complete and the building shell still open, winter snowmelt and spring runoff (March–April 2026) create stormwater discharge and erosion risks. A SWPPP violation or NOV from the Utah Division of Water Quality can result in fines and a stop-work order. Likelihood 2 (spring runoff is seasonal and predictable; SWPPP controls should be in place); Impact 2 (fines, remediation, minor schedule disruption). | Low | 4 | $10,000 | 2 | Superintendent

## Budget
IN PROJECT AI - BUDGET IQ
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
At Risk |  |  | $4,977,000 |  | $-157,000 | 0.839 / 0.872
COST HEALTH |  |  | FORECAST AT COMPLETION - EAC |  | VARIANCE - -3.26% | CPI / SPI - earned value
Budget health and earned value
Metric | Value | Meaning | Visual
Original budget | $4,820,000 | Baseline value used for control comparison.
Current budget | $4,820,000 | Approved budget after known changes.
Forecast at completion | $4,977,000 | Expected final cost based on current evidence.
Variance | $-157,000 (-3.26%) | Overrun pressure to review.
Contingency remaining | $276,000 | Available contingency after current exposure.
EAC / ETC | $5,748,152 / $2,760,152 | Forecast at completion and estimate to complete.
TCPI | 1.041 | Required cost efficiency to finish at target.
Budget-at-risk register
Item | Driver | Likelihood | Exposure
HVAC Equipment (Chiller, Boiler, Controls) | Material escalation (8–10% above Q3 2025 baseline); long-lead procurements locked in at elevated pricing. CO-005 imaging-suite add ($52.4K pending) will push category $140K over budget if approved. | High | $87,400
Curtain Wall & Window Systems | Design coordination delays (CO-006 detail revision, $9.2K pending); supply-chain lead-time extension (12–16 weeks); field installation productivity 30% below estimate due to complex flashing details at floor/roof intersections. | High | $33,600
Structural Steel Connections | Material escalation (Q4 2025 – Q1 2026 pricing); field welding/inspection inefficiencies on moment connections; re-work anticipated on 3–4 critical nodes per structural QA findings in Month 4. | High | $49,600
Building Envelope Rework & Scope Creep | Discrepancy between billed (18% = $104K) and field-complete (~12%). Possible over-billing, design changes, or failed first-time-right on flashing/sealing. Requires field audit before next milestone. | Medium | $40,000
General Conditions Extended Mobilization | Project management overhead, site office, and supervision trending 2.7% over budget. Schedule compression in Finishes phase (Sep 2026) may require 2–3 week contract extension, adding $8–12K to general conditions. | Medium | $13,000
Pending Change Orders (CO-005, CO-006) | CO-005 (HVAC, $52.4K) and CO-006 (Envelope, $9.2K) both pending Owner/Designer approval. If approved without scope trade-off, will consume 22% of remaining contingency. | High | $61,600
Finishes Material Lead-Time Risk | Millwork and custom fixtures on 14–18 week lead-time from order. If orders delayed 3+ weeks, final-phase labor compression and potential schedule slip into October 2026 (triggering LD at $2,500/day). | Medium | $25,000
Cash-flow readout
Period | Planned | Actual / forecast | Delta
Month 1 (Sep 2025) | $280,000 | $265,000 | $-15,000
Month 2 (Oct 2025) | $630,000 | $650,000 | $20,000
Month 3 (Nov 2025) | $1,010,000 | $1,070,000 | $60,000
Month 4 (Dec 2025) | $1,370,000 | $1,480,000 | $110,000
Month 5 (Jan 2026) | $1,780,000 | $1,945,000 | $165,000
Month 6 (Feb 2026) | $2,200,000 | $2,370,000 | $170,000
Month 7 (Mar 2026) | $2,560,000 | $2,735,000 | $175,000
Month 8 (Apr 2026) | $2,900,000 | $3,090,000 | $190,000
Month 9 (May 2026) | $3,230,000 | $3,435,000 | $205,000
Month 10 (Jun 2026) | $3,540,000 | $3,760,000 | $220,000
Month 11 (Jul 2026) | $3,820,000 | $4,055,000 | $235,000
Month 12 (Aug 2026) | $4,070,000 | $4,320,000 | $250,000

## Schedule
IN PROJECT AI - SCHEDULE IQ
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
12 months (52 weeks from 2025-09-14 to 2026-09-30) |  |  |  | 13 months (56–57 weeks) |  |  |  | 4–5 weeks (~2.5 days per week, or ~$50k–$75k in cost/schedule reserve) |  |  |  | -
BASELINE DURATION - baseline |  |  |  | RISK-ADJUSTED DURATION - forecast |  |  |  | RECOMMENDED BUFFER - schedule risk |  |  |  | CRITICAL PATH - status
Schedule Gantt
Milestone | Target | Predecessor | Status | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Notice to Proceed | 2025-09-14 | N/A | - | X
Mobilization Complete | 2025-09-28 | Notice to Proceed | - |  | X
Site Grading & Utilities Complete | 2025-11-10 | Mobilization Complete | - |  |  | X
Foundations Complete | 2026-01-15 | Site Grading & Utilities Complete | - |  |  |  | X
Structural Steel Erection Complete | 2026-03-20 | Foundations Complete | - |  |  |  |  | X
Building Envelope Substantially Complete | 2026-06-15 | Structural Steel Erection Complete | - | [5 empty] | X
MEP Rough-In Complete | 2026-07-15 | Building Envelope Substantially Complete | - | [6 empty] | X
Interior Finishes Complete | 2026-09-01 | MEP Rough-In Complete | - | [7 empty] | X
Systems Commissioning Complete | 2026-09-22 | Interior Finishes Complete | - | [8 empty] | X
Punch List Complete | 2026-09-28 | Systems Commissioning Complete | - | [9 empty] | X
Substantial Completion / Certificate of Occupancy | 2026-09-30 | Punch List Complete | - | [10 empty] | X
Procurement and schedule concerns
Item | Need-by | Lead time | Risk | Action
Structural Steel (Beams, Columns, Connections per RFI-047) | - | 12–14 weeks | - | -
HVAC Units (Rooftop Units, Supply/Return Equipment) | - | 10–12 weeks | - | -
Electrical Switchgear & Distribution Panels | - | 10–12 weeks | - | -
Medical Gas System Equipment (Pipeline, Regulators, Outlets) | - | 8–10 weeks | - | -
Curtain Wall / Glazing Panels | - | 12–14 weeks | - | -
Roofing Materials & Waterproofing System | - | 6–8 weeks | - | -
Doors, Frames & Hardware (Exterior & Interior) | - | 8–10 weeks | - | -
Drywall & Framing Materials (Gypsum, Studs, Joint Compound) | - | 4–6 weeks | - | -
Flooring Materials (Tile, VCT, Carpet, Resilient Panels) | - | 6–8 weeks | - | -
Plumbing Fixtures & Rough-In (Sinks, Toilets, Drains, PEX/Copper Tubing) | - | 6–8 weeks | - | -
Building Automation System (Controls, Sensors, Actuators) | - | 8–10 weeks | - | -
Elevators (if multi-story) | - | 14–16 weeks | - | -

## Documents
IN PROJECT AI - DOCUMENT IQ
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
Document | Classified Type | Confidence
budget_cost_report.csv | budget | 0.95
change_order_log.csv | change_order_log | 0.99
commissioning_plan.txt | commissioning_doc | 0.92
daily_report.txt | daily_report | 0.97
inspection_report.txt | inspection_report | 0.98
lien_waivers.txt | lien_waiver | 0.99
pay_application_03.csv | pay_application | 0.99
prime_contract.txt | contract | 0.99
rfi_log.csv | rfi_log | 0.99
schedule_lookahead.csv | schedule | 0.99
schedule_of_values.csv | sov | 0.98
site_safety_plan.txt | safety_plan | 0.99
submittal_log.csv | submittal_log | 0.99

## Quality
IN PROJECT AI - QUALITY IQ
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
Pattern | Freq | Locations | Trades | Severity | Likely Root Cause
Cold joints in cast-in-place slab pours | 3 | Zone B Level 2 | Concrete | high | Improper pour sequencing and inadequate joint management; concrete losing workability between placement cycles or insufficient vibration at slab edges and transitions.
Safety protocol non-compliance in Zone B | 3 | Zone B stairwell and general area | GC/All trades | high | Insufficient fall-protection enforcement and supervision in Zone B; three near-misses in 14 days suggests systemic gaps in daily toolbox talks or worker accountability.
Drywall crew under-staffing and quality gaps | 2 | Level 1 north wing | Drywall | medium | Subcontractor staffing shortage persisting 3+ weeks; screw spacing non-compliance and hanging delays indicate insufficient labor availability or quality oversight during installation.

## Submittals
IN PROJECT AI - SUBMITTAL IQ
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
ID | Spec | Description | Status | Days Overdue | Severity | Note
SUB-038 | 23 73 00 | Air Handling Units | overdue | 50 | critical | AHU submittal overdue 50 days as of 2026-02-28. Blocks MEP rough-in, mechanical trim-out, and commissioning; 6–8 week lead time from approval to delivery adds schedule risk to mechanical systems completion by 2026-09-30.
SUB-031 | 08 44 00 | Curtain Wall / Glazing Shop Drawings | missing | 0 | critical | Curtain wall shop drawings not submitted (required return: 2026-02-15, now 13 days past due as of 2026-02-28). Envelope closure is critical path; 6-week fabrication + installation lead time blocks facade work and weather seal; failure to submit within 7 days will delay building closure into late 2026.
SUB-045 | 22 40 00 | Plumbing Fixtures | stale | 0 | high | Plumbing fixtures stale 44 days (last activity 2026-01-15); required return was 2026-02-05 (23 days past due). No approval blocks rough-in completion and fixture rough coordinations; MEP coordination risk ahead of drywall closure.
SUB-035 | 09 51 00 | Acoustical Ceilings | in_review | 0 | medium | In review since 2026-02-03 (25 days); required return 2026-02-20 (8 days overdue). Moderate schedule impact if approval delayed further; dependent on structural/MEP/fire-rated substrate clearance.
SUB-040 | 26 51 00 | Lighting Fixtures | in_review | 0 | medium | In review since 2026-02-25 (3 days); required return 2026-03-01 (approaching). LED/fixture coordination required with electrical rough-in; monitor for approval by early March.
SUB-042 | 09 29 00 | Gypsum Board Assemblies | approved | 0 | low | Approved 2026-03-01, on schedule. Supports drywall release and fire-rated assembly execution.
SUB-001 | 03 30 00 | Concrete Mix Design | approved | 0 | low | Approved 2025-10-12, closed. Concrete placement and curing complete.
SUB-014 | 05 12 00 | Structural Steel Shop Drawings | approved | 0 | low | Approved 2025-12-08, closed. Steel erection complete.
SUB-022 | 07 41 00 | Roofing System | approved | 0 | low | Approved 2026-01-22, on schedule. Roofing installation underway or complete.

## RFIs
IN PROJECT AI - RFI IQ
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
RFI | Subject | Days Open | Impact | Priority | Blocked Activities
RFI-047 | Steel connection detail at grid C-4 | 20 | both | 1 | A400 – Steel erection
RFI-045 | Electrical panel location conflict with ductwork | 15 | both | 2 | MEP rough-in coordination – east wing
RFI-041 | Door hardware schedule clarification | 24 | neither | 3
RFI-049 | Curtain wall anchor embed depth | 7 | cost | 4
RFI-052 | Fire damper at corridor smoke barrier | 1 | schedule | 5
RFI-051 | Finish floor transition detail | 3 | neither | 5

## Change Orders
IN PROJECT AI - CHANGE IQ
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
CO | Description | Amount | Initiator | Status | Severity | Reason Flagged
CO-005 | HVAC capacity increase for imaging suite | $52,400 | owner | Pending | high | Largest single CO; pending 10 days as of reporting date; imaging suite capacity is critical-path MEP system for occupancy
CO-002 | Owner-requested upgrade to lobby finishes | $46,000 | owner | Approved | medium | Owner-directed scope growth representing 24.7% of total CO value; non-essential finishes may signal scope creep vs. baseline scope clarity
CO-001 | Added site retaining wall (differing site condition) | $38,500 | unforeseen | Approved | medium | Largest unforeseen condition; retaining wall is structural and may affect grading/drainage schedule and future site work
CO-004 | Additional fire-rated assemblies per AHJ | $21,300 | unforeseen | Approved | medium | AHJ-driven scope; indicates design or code-compliance gap at plan review; assess whether submittal log and inspection reports flagged fire rating earlier

## Action Items
IN PROJECT AI - ACTION ITEMS
Cedar Ridge Medical Office Building ¦ Generated 2026-08-25
Priority | Action | Owner | Due | Impact | Source
1 | Hold Cost-Control Board Meeting; Formalize Contingency Allocation Against P80 Risk Exposure ($498K) and Establish Change-Order Approval Gate | Project Manager & Owner Representative | 2026-02-26 | $222,000 | budget
1 | Issue Stop-Work Order and Execute Fall Protection Plan for Steel Erection (Activity A400) | Safety Manager & Project Superintendent | 2026-02-25 | $185,000 | safetyPlan
1 | Engage Commissioning Authority via RFP; Target Contract Execution Within 14 Days | Project Manager | 2026-03-07 | $175,000 | commissioning
1 | Issue Formal Cure Notice to Drywall Subcontractor; Enforce 8–10 Personnel Minimum by March 7 or Terminate Contract | Project Superintendent | 2026-02-25 | $140,000 | risk
1 | Conduct Root-Cause Investigation into Zone B Concrete Cold Joints (3 NCRs in 14 Days); Issue Revised Pour-Sequencing Plan and QC Protocol | Project Engineer & Concrete Subcontractor | 2026-03-03 | $120,000 | qcRollup
1 | Escalate RFI-047 (Steel Connection Detail, Grid C-4) to Architect with 72-Hour Response Deadline | Project Manager | 2026-02-27 | $95,000 | rfis
1 | Withhold Payment on Mechanical ($62.5K) and Electrical ($26.5K) Subs Until Conditional Progress Lien Waivers Received | Cost Engineer & Project Manager | 2026-02-28 | $88,970 | lienWaivers
1 | Issue Corrected Owner Communication Addressing $88.97K Lien-Waiver Hold and $23.1K Envelope Overbilling Discrepancy | Project Manager | 2026-02-28 | $88,970 | ownersReport
1 | Remediate Critical Life-Safety Deficiencies (Fire-Stop Junction Box & Fire-Caulk NCR-019); Complete Re-Inspection Within 5 Days | Electrical Contractor & Superintendent | 2026-03-03 | $55,000 | punchList
2 | Issue Hard Submittal Deadline (March 7) for Curtain-Wall Shop Drawings (SUB-031), AHU (SUB-038), Plumbing Fixtures (SUB-045); Authorize Local Procurement if Deadline Missed | Project Manager | 2026-03-07 | $95,000 | submittals
2 | Schedule Emergency MEP Coordination Meeting to Resolve CO-005 HVAC Imaging-Suite Scope and Expedite AHU Submittal (SUB-038) Review | Project Manager & MEP Coordinator | 2026-03-01 | $95,000 | changeOrders
2 | Issue Expedited RFQs for Test & Balance Contractor and Fire Alarm AHJ Acceptance-Test Scheduling; Target T&B Contract Within 14 Days | MEP Coordinator & Safety Manager | 2026-03-07 | $75,000 | commissioning
2 | Establish Weekly RFI/Submittal War Room (Mondays 10 AM) with Design Team, GC, and Trades; Implement 72-Hour Response Enforcement for Overdue Items | Project Manager | 2026-03-03 | $50,000 | rfis
2 | Implement Project-Control Baseline with Earned-Value Tracking (PV, AC, EV by Phase); Begin Weekly SPI/CPI/EAC Variance Reporting | Project Controls Manager | 2026-03-10 | $0 | report
3 | Quantify Cumulative Cost and Schedule Impact of Current Delays; Prepare Change-Order Estimate for Owner Submission (General Conditions, RFI Re-Work, Expedited Procurement) | Project Controls Manager & Estimator | 2026-03-07 | $120,000 | budget

## Source (hidden)
Project | {"name":"Cedar Ridge Medical Office Building","gc":"In Project LLC","owner":"Wasatch Health Partners","contract_value":4820000,"phase":"Construction","phase_pct":58,"last_run_at":"2026-08-25T02:32:22.899Z"}
KPIs | {"health_score":29,"health_delta":null,"risk_exposure_usd":1125085,"risk_exposure_delta":null,"confidence_index":67,"projected_slip_days":39,"slip_delta":null}
Classifications | budget_cost_report.csv=budget(0.95); change_order_log.csv=change_order_log(0.99); commissioning_plan.txt=commissioning_doc(0.92); daily_report.txt=daily_report(0.97); inspection_report.txt=inspection_report(0.98); lien_waivers.txt=lien_waiver(0.99); pay_application_03.csv=pay_application(0.99); prime_contract.txt=contract(0.99); rfi_log.csv=rfi_log(0.99); schedule_lookahead.csv=schedule(0.99); schedule_of_values.csv=sov(0.98); site_safety_plan.txt=safety_plan(0.99); submittal_log.csv=submittal_log(0.99)
Scoring buckets | {"risk":30,"budget":3,"schedule":25,"docs":3,"quality":10}
Doc completeness | {"index":67,"expected":["contract","drawing_set","spec_book","budget","schedule","sov"],"providedTypes":["budget","change_order_log","commissioning_doc","daily_report","inspection_report","lien_waiver","pay_application","contract","rfi_log","schedule","sov","safety_plan","submittal_log"],"missingTypes":["drawing_set","spec_book"],"providedCount":4,"expectedCount":6}
Module run status
classifier (pipeline) | success
risk (agent) | success
budget (agent) | success
planning (agent) | success
report (agent) | success
document-review (agent) | success
submittals (module) | success
rfis (module) | success
changeOrders (module) | success
punchList (module) | success
safetyPlan (module) | success
payApp (module) | success
sov (module) | success
commissioning (module) | success
qcRollup (module) | success
lienWaivers (module) | success
ownersReport (module) | success
synthesis (pipeline) | success
weeklyDelta (module) | skipped - no prior run for this project — nothing to compare
executive_briefing (pipeline) | success
action_items (pipeline) | success